## Project Plan and Gantt
Project Name | Quản Lý Bán Vé Xem Phim
Project Manager | Võ Duy Tân
Project Deliverable
Scope Statement:
Start Date | 2016-08-27
End Date | 2015-10-10
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Võ Duy Tân | 2016-08-27 | 2016-08-27 | 0 | Complete
Agree on objectives | Võ Duy Tân | 2016-08-27 | 2016-08-27 | 0 | Complete
Detailed Reqs. | Võ Duy Tân | 2016-08-27 | 2016-08-27 | 0 | Complete
Techincal Reqs. | Đồng Duy Thiện | 2016-08-27 | 2016-08-28 | 1 | Not started
DB Development | Đồng Duy Thiện | 2016-08-29 | 2016-08-30 | 1 | Not started
Connect DB | Võ Duy Tân | 2016-08-31 | 2016-09-02 | 2 | Not started
Insert/Update/Query | Võ Duy Tân | 2016-09-03 | 2016-09-06 | 3 | Not started
API Development | Đồng Duy Thiện | 2016-09-07 | 2016-09-09 | 2 | Not started
Function 1 | Đồng Duy Thiện | 2016-09-10 | 2016-09-16 | 6 | Not started
Function 2,… | Võ Duy Tân | 2016-09-17 | 2016-09-21 | 4 | Not started
UI Client | Team | 2016-09-22 | 2016-09-23 | 1 | Not started
Testing | Team | 2016-09-24 | 2016-09-26 | 2 | Not started
Dev. Complete | Team | 2016-09-27 | 2016-09-29 | 2 | Not started
Hardware Config. | Team | 2016-10-01 | 2016-10-03 | 2 | Not started
System Testing | Team | 2016-10-03 | 2016-10-05 | 2 | Not started
Launch |  | 2016-10-10 | 2016-10-10 | 0

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address
Võ Duy Tân | Team leader | 1. Make the plan of the project. 2. Assign task for your member. 3. Analysis & design the system. 4. Code. 5. Write document | mrblueshadow01@gmail.com
Đồng Duy Thiện | Developer | 1. Design GUI/database. 2. Code. 3. Test | duelisttazzker@gmail.com

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team